## Sheet1
week/date | time (estimated days) | Event/Task
2023-03-13 | 0.03 | reached out to start project/first meeting
2023-03-16 | 0.09 | first meeting: primary agreement - re-do analyses w/ now clean data; no agreement on 3 papers in notes - noted that I would prepare methods/results, some students will want to be 1st author, some wont.
2023-03-16 |  | get (identifiable) data
2023-03-16 |  | received thesis (rurality)
2023-03-17 | 0.5 | reviewed fMRI behavioral decision making protocols and document (sent email back about it)
2023-03-17 |  | rurality data by school received
3/20/2023 - 3/24/2023 | 2 | review rurality thesis and outline analyses, review initial dataset (labels, definitions) - no analyses due to IRB, fix rurality by school data - original did not align with dataset
2023-04-04 | 0.03 | eamil check-in about IRB (holding off until hear back)
2023-05-08 | 1 | initial attempt to replicate rurality thesis
May 9th | 0.09 | 1st data meeting
2023-05-09 |  | get de-identified data
2023-05-09 |  | get TTE data
05/12/2023 - 05/16/2023 | 2.5 | create r project for christina thesis (eating duration) and initial analyses, figures, tables, and generate PDF output
May 16th | 0.9 | christina meeting pdf sent for all initial results
2023-05-17 | 1.5 | segment models by school level, redo demo tables, double check zero inflated model parts, add interpretation to pdf and clean up pdf
May 18th | 0.03 | updated results sent (10 pm)
May 18th | 0.25 | check concerns about eating duration and lunch duration colinearity
May 18th | 0.1 | coverted and sent updated databases to Meg
May 23rd | 0.09 | christing/meg meeting
5/25/23-5/30/23 | 1.5 | update tables, output, add interpretation and confirm all results
2023-05-30 | 0.03 | sent updated results pdf with additional interpretation language
2023-07-05 | 0.2 | individual meeeting with christina
2023-07-06 | 0.25 | review thesis draft
2023-07-06 | 0.5 | start editing methods
7/10/23-7/14/23 | 1 | updates to thesis after defense, additional analyses, additional interpretation, updated pdf several times
2023-07-18 | 0.03 | email check in about TTE paper, said we will discuss more due to my concern of it being outside my field
2023-07-21 | 0.5 | check TTE interaction with school - lots of trouble converging models
7/24/2023 - 7/28/2023 | 1 | draft methods/results, make all tables
7/24/2023 - 7/28/2023 | 2 | identified bimodel (0/1 inflation), research on solutions/alternatives and implimentations
2023-07-27 | 0.09 | meeting about waste distribution - presented 3 alternative approaches w/ pros and cons
7/31/23 - 8/4/23 |  | OUT - Vacation
8/7/23-8/1/23 | 0.25 | edits and updates to methods/results
2023-08-14 | 0.03 | sent initial draft of methods/resutls
8/14/2023 - 8/18/23 | 1 | check N with neg TTE, update demo with restricted sample, re-run models w/out neg TTE
2023-08-18 |  | results/methods comments received
08/21/2023 - 08/25/2023 | 1.5 | edit methods/write analytic plan, update all results with new models (w/o neg TTE), remake all tables
2023-08-21 | 0.5 | do the separate analyses for the waste, write up interpretation
2023-08-22 | 0.03 | sent intial findings with the proposed 2-step approach
8/28/23 - 9/1/23 |  | OUT - COVID
2023-08-29 |  | received feedback via email to proceed with 2-step approach
9/11/23 - 9/15/23 | 1 | update/clean up paper, add 2-step model for waste, update tables
9/18/23 - 9/22/23 |  | OUT - Vacation
2023-09-19 | 0.03 | sent out clean methods/results to group
total weeks | 32 weeks |  | weeks since received de-identified data: | 22 weeks
Vacation weeks | 2 weeks |  | Vacation weeks | 2 weeks
total days | 20.55 |  | total days | 20.55
11 weeks left so need about 2 days per week to meet covered time
date | Hours | event/task
2023-10-17 | 0.75 | meeting
2023-10-17 | 2.5 | rurality analyses
2023-10-17 | 0.5 | adjust prop waste (was using fv_post — needed to change to use (fv_pre - fv_consumed to handle the way fv_pre > fv_post were only change in consumed, not fv_post
2023-10-17 | 0.5 | double analyses code for TTE
| Hours | Days
running total after meeting (9/26) | 4.25 | 0.53125